## Actions
Project |  |  | Actions
Date
Author
Ref | Date Added | Action | Responsible | Function | Status | Due Date | Comments
1 | 2021-08-16 | The PCG will need to include the following key groups / people: o SOPA / Quay Centre (Steven) o BNSW (Maria / Luisa) o LOC (Lorraine) o MI (Emma) o Netball Central (Ben) | Emma Collyer | PCG | Closed | Closed | 07/09 - PCG to be established ASAP. The group will need to approve the project objectives which will inform the Pre Project Evaluation. The aim is to have the first meeting week commencing 20/09. 14/09 - Following the kick off meeting, the commencement of the PCG will be on hold until the new scope is finalised. MN and SD noted the PCG only need to be EC/LM and NG. EC has since reviewed the OoS requirements and the PCG is outlined as 'governance arrangement and group of persons to oversee the delivery of the Project. It ensures delivery of scope, oversees risk management, and ensures the Project stays within Budget. It will involve key project stakeholders, including You and the Department' This will need t be established either fortnightly or monthly with MN, SD and OoS for key oversight of the project. 28/09 - LM was contacted by the OoS following a email quesation about PCG members. The OoS has advise that a PCG is not required for either Bathurst or Quay Centre.
2 | 2021-08-16 | Andrew from Bathurst is seeking 3 quotes, preferably from the contractors recently used by the Council to provide a firm pricing for the Funding Agreement | Andrew James | Procurement - Refurbishment | Overdue | 2021-11-23 | 07/09 - Council have now indicated that a DA is possibly required to complete the works. AJ and MN are working with council to determine the requirement. AJ to provide an UPDATE on the status of the 2 refurbishment 14/09 - LMC has a catch up with AJ this week and will provide an update. 21/09 - Still waiting on quotes. 01/11 - AJ is working with the council town planner to confirm a scope within the complying development. 16/11 - LM to follow up with AJ.
6 | 2021-08-16 | Maria to have a discussion with Stephen from Quay Centre about the project, seeking final quotes and indicative timelines from the approved contractors and his availability for a kick off meeting Thursday 02/09. | Maria Nordstrom | Initiation | Closed | Closed | 07/09 Kick off meeting early next week to discuss facility usage, updated scope, contractors, program, PMP and PCG.
7 | 2021-08-16 | Final Scope for Quay Centre to be confirmed (FIBA sized changeroom requirements) | Maria Nordstrom | Initiation | Closed | 2021-10-26 | 07/09 - Scope change has been confirmed and MN is working with SD to finalise these. Update to be provided at kick off meeting. 14/09 - NG is documenting the scope and liaising with contractors 21/09 - Final scope being developed. NG confirmed works would occur in the following areas: Changeroom 3 – 9 (These will be made into 4 dual shower / change room areas. Non wet areas will be carpeted) Changeroom 1 & 2 - Vanity & pationing and vanity only. Hockey 1 – 3 Changerooms Changeroom A, B, C, D Main Reception Toilets - Male Main Reception Toilets – Female Main Reception Toilets – Unisex 28/09 - NG to provide a summary overview of the scope items for each area for the funding agreement by Thursday. 05/10 - Scope has been confirmed, juist waiting on budget to align and ensure we ave enough funding. 14/10 - Still awaiting partitioning quote. 19/10 - NG is due to speak with ARA today. In the absence of a quote, the contractor has been asked to provide an inidicative price based on their knowledge of the work. 26/10 - Being finalised and due today. 02/11 - Final scope has been confirmed with Hockey Pitch 3 removed from scope. This will mean the 2 chnagerooms 1 and 2 on the sourthern side will be upgraded and 3 and 4 will remain as is.
14 | 2021-09-28 | SOPA contractors are finalising quotes for the revised Scope | Neil Gillies | Procurement - Refurbishment | Closed | Closed | 28/09 - NG is waiting on 2 final quotes, including the one for the pationing. These are to be sent to LM and EC before Friday. Pationing contractor only went to site Monday 27/09 so if the quote isnt ready by Friday, we may have to make an assumption on the budget for the final scope without it. 05/10 - Still awaiting the pationing quotes 14/10 - These are due today. 19/10 - Still awaiting the partitioning quote. 02/112 - Completed.
15 | 2021-09-28 | The current dual changerooms 1, 2, 5, 6 have spilt system air conditioning. This might be required for changeroom 3 and 9. | Neil Gillies | Procurement - Refurbishment | Closed | Note | 28/09 - NG to get some quotes. This may be able to be convered in the SOPA budget. 05/10 - This will need to be included in the grant funding, LM to update scope and budget. Cost of each unit is $14,250. 14/10 - These have been included in the budget. 16/11 - THis is included in the works and can be removed.
16 | 2021-10-14 | Video Board upgrade - LED Australia | Emma Collyer | Procurement - Equipment | In Progress | 2021-12-07 | 14/10 - EC to call LED Australia and get final quote for work. 19/10 - EC spoke with Myles from LED Australia. He will honour the price provided for the proposal to upgrade the Quay Centre Videoboards for $34,670. Can be ordered when we are ready. 26/10 - EC to get a firm quote on the engineering required. $5k was allowed for in the proposal, however this may be close to $10k. 02/11 - There is a concern that there may be a double up in scope between RMA and LED Australia for the controllers and shock clockes. LM discussing with Roger from RMA to clarify. A meeting with both suppliers will need to be arrange to ensure the right integration is able to be achieved once the video upgrade is completed. 09/11 - What was assumed to be included in the original price (new screen and upgrade to existing screen) is not correct. The $34,650 was for upgrade size only. NG advised that SOIPA dont want the screens larger permanently, that it should only be for the event then removed. They also dont have anywhere to store the spare modules should a new screen be installed. LM to discuss with MN. Options to be sought from Myles from LED AUstralia which will also need to include putting the screens back to original size post event. 16/11 - At RMA we don't know what LED Australia are providing, however we can guarantee RMA will provide an HDMI output to feed signal for the LED Australia system' are you happy with this response. 30/11 - MN has decded that this isn't worth the cost and there is no storage space. it is to be removed fromt he scope. LM to chase email confirmation.
17 | 2021-10-14 | Fridges and Hospitality FF&E | Luisa Mastrangelo-Clarke | Procurement - Equipment | In Progress | 7/12/121 | 14/10 - LM to confirm with MN if these are still to be included in the scope. 19/10 - LM and EC to sit down with MN and confirm sope once all pricing is in. 02/11 - Still to be confirmed, once clarity on budget is received.
18 | 2021-10-19 | Netball Central Scope to be confirmed. Meeting with Ben Jessemer to be arranged to clarify scope and requirements. | Emma Collyer | Procurement - Equipment | In Progress | 2021-12-07 | 19/10 - NG to introdcue via email and EC and LM to meet with BJ ASAP. 26/10 - EC has met with Ben and Ari. There might be some opportunity to reduce the scope of the scoreboards to just supply shock clocks. Ben advised they have an LED screen on the showcourt and a scoreboard on court 5. He mentioned they preferred drop down back boards, however he believes this was due to the FIBA level 1 requirement. We will need to get RMA to quote installing anchor points on the floor of the showcourt as well. Ben is going to send through the photos of what is there currently. We also need to confirm when installation will need to be. BJ doesnt believe it will be until later in 2022. 30/11 - LM to chase RMA for the quote.
21 | 2021-10-26 | Timing is starting to become critical. | Emma Collyer | Installation | Overdue | 2021-11-22 | 26/10 - EC advised that timing is becoming critical if we are going to meet the February or March timing. 02/11 - RMA is providing an update on delivery timeframe. NG will confirm timing with contractors. 09/11 - The project has now been confirmed for completion by mid March. We will still need to order the equipment as a matter of urgency. LM to confirm with Roger the latest possible date we can order to meet the march deadline. 16/11 - Hoping to have the equipment ordered this week and construction to start Monday 22/11.
23 | 2021-10-26 | OoS has now requested the facility usage data for Quay Centre. | Luisa Mastrangelo-Clarke | Milestone Reporting | Closed | Closed | 26/10 - LM to work with Alex to input the data into the OoS spreadsheet. 02/11 - This is due to be finalised today. 16/11 - this was completed and submitted to the OoS
24 | 2021-11-02 | BNSW has advised that they have now been awarded the World Cup Qualifiers on February 13, 2022. The works and equipment are required to be completed prior to this. | Luisa Mastrangelo-Clarke | Procurement - Refurbishment | Closed | Closed | 02/11 - LM to confirm which facilities completion are critical for the event should the contractor not be able to bring forward his timeframe and meet the new date. 09/11 - This event is now been relocated.
25 | 2021-11-02 | BNSW to provide a written approval to SOPA for the refurbishment works | Luisa Mastrangelo-Clarke | Procurement - Refurbishment | Closed | Closed | 02/11 - MN to provide written approval for the refurbishment works to NG from SOPA. 09/11 - This will be completed once the signed agreement is executed. 16/11 - Executed agreement has been distributed and approval email sent from MN.

## Lookup
| Initiation | Name
Open | Milestone Reporting | Name
Closed | PCG | Name
Overdue | Procurement - Equipment | Name
In Progress | Procurement - Refurbishment
Critical | Installation
On Hold | Construction
Note | Closure